## Slide 1
Here are 6 types of subcontractors that you need to organise a schedule for. Read through the subcontractors and make sure you understand what they do and the order of work.
Developing Experts Copyright 2026 All Rights Reserved
VWE: Morgan Sindall Construction – Day 3
Handout 5 – Subcontractor schedule
Trade | Colour | Task | Duration per floor | Notes
Excavator/ groundworkers | 🟤 Brown | Excavate foundations and install drainage | Floor 0 (basement) only: 5 days | Only ground level excavation; no repeat per floor
Concrete finishers | 🟢 Green | Place slabs | 1 floor = 3 days | Staggered start on each floor, starting with floor 1 once foundations are secure
Steel erectors | 🔴 Red | Erect structural frame | 1 floor = 2 days | Can start once concrete slabs are placed
Electricians | 🟡 Yellow | Install containment and cabling | 1 floor = 2 days | Can follow steel and slab installation
Plumbers | 🔵 Blue | Install pipework | 1 floor = 2 days | Can follow steel and slab installation
Carpenters/ joiners | 🟠 Orange | Install stud walls and doors | 1 floor = 3 days | Usually finishes interior; can start after slab and M&E services installed

## Slide 2
Developing Experts Copyright 2026 All Rights Reserved
VWE: Morgan Sindall Construction – Day 3
Handout 5 – Subcontractor schedule
Subcontractor 6 week schedule
Using the 6 week schedule, create a colour-coded plan showing when each subcontractor team will work on each floor over the next six weeks. The first subcontractor has already been scheduled as an example. Note: The project does not need to be fully completed within this six-week period.
 | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  | 
Level 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 3
Developing Experts Copyright 2026 All Rights Reserved
VWE: Morgan Sindall Construction – Day 3
Handout 5 – Subcontractor schedule
According to your schedule, when will Level 1 be complete? _________________________________________________________
According to your schedule, what will still need to be done on Level 7 by the end of the 6 weeks? _________________________________________________________
According to your schedule, how many days of work will the steel erectors need to be billed for? _________________________________________________________
According to your schedule, which subcontractor will have finished all their work by the end of the 6 weeks? _________________________________________________________
Why do you think no subcontractors could start their work until the groundworkers had finished theirs? ______________________________________________________________________________________________________________________________________________________________________________________________________
Challenge: According to your schedule, when will all 8 levels be complete? ___________________________________________________________________________________________________
Challenge: In Week 3, the concrete finishers cancel work due to sickness. How does this affect your timeline? ______________________________________________________________________________________________________________________________________________________________________________________________________
When making a schedule like this, what other factors do you think need to be taken into consideration? ______________________________________________________________________________________________________________________________________________________________________________________________________
Answer the following questions to show your understanding of the scheduling task.

## Slide 4
Developing Experts Copyright 2026 All Rights Reserved
VWE: Morgan Sindall Construction – Day 3
Handout 5 – Subcontractor schedule Answers
Subcontractor 6 week schedule
Here is an example of what a completed schedule might look like. Please note that the electricians (yellow) and the plumbers (blue) can be swapped around or even work alternative days on the same level.
 | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  | 
Level 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Level 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 5
Developing Experts Copyright 2026 All Rights Reserved
VWE: Morgan Sindall Construction – Day 3
Handout 5 – Subcontractor schedule Answers
According to your schedule, when will Level 1 be complete? By Tuesday Week 4
According to your schedule, what will still need to be done on Level 7 by the end of the 6 weeks? Installing the pipework (plumbers) OR installing containment and cables (electricians) AND installing stud walls and doors (carpenters/joiners)
According to your schedule, how many days of work will the steel erectors need to be billed for? 15
According to your schedule, which subcontractors will have finished all their work by the end of the 6 weeks? Excavator/groundworkers and concrete finishers
Why do you think no subcontractors could start their work until the groundworkers had finished theirs? Sample answer: No subcontractors could start work until the groundworkers had finished because the foundations and site preparation must be completed first. Without a stable base, it would not be safe or possible for other teams to begin their work.
Challenge: According to your schedule, when will all 8 levels be complete? All 8 levels will be completed by Wednesday Week 8 if there are no delays.
Challenge: In Week 3, the concrete finishers cancel work due to sickness. How does this affect your timeline? Sample answer: If the concrete finishers cancel work in Week 3, the plumbers, electricians and carpenters/joiners will be delayed by a week, as they depend on the concrete slabs being in place to start their work. This means the entire project will be delayed by a week.
When making a schedule like this, what other factors do you think need to be taken into consideration? Sample answer: When making a schedule, you need to consider factors like weather delays, material and equipment availability, staff absences, safety requirements, and contingency budgets.