## Slide 1
The transcript below shows a client progress meeting that took place at 17 Columbus Courtyard. Read the transcript and highlight the key information. Then use the template on the next page to record the minutes from the meeting.
Developing Experts Copyright 2026 All Rights Reserved
VWE: Morgan Sindall Construction – Day 3
Handout 1 – Taking minutes
Project: 17 Columbus Courtyard Date: 12 March 2025 Attendees:
Fergus (Client)
Robert (Project Manager)
Shayne (Site Manager)
Nick (Quantity Surveyor)
Megan (Design Manager)
Robert: Good morning, everyone. Thank you for attending the monthly progress meeting for 17 Columbus Courtyard. The purpose of today’s meeting is to review progress on site, discuss any issues, and agree on next steps. By the way, does anyone want coffee? I think the machine is working this time.
Shayne: Construction is currently on schedule. The groundworks have been completed, and the steel frame is 80% installed. We expect the frame to be fully completed by the end of next week, weather permitting. The team has been enjoying the warmer weather while working on site, though.
Fergus: That’s good to hear. Are there any delays we should be aware of?
Shayne: There was a minor delay last week due to high winds, which paused crane operations for one day. We’ve made up this time by extending working hours on Friday.
Robert: Health and safety inspections are positive, with no reportable incidents this month. I have also noticed a few new birds nesting near the site entrance -they’re harmless but very noisy in the morning.
Megan:
Ah, yes! I heard them on my way in this morning.
Robert:
Nick, can you give an update on costings and budgets please?

## Slide 2
Developing Experts Copyright 2026 All Rights Reserved
VWE: Morgan Sindall Construction – Day 3
Handout 1 – Taking minutes
Nick: We are doing well; the project is currently within budget. Steel prices have increased slightly, which could affect future phases if prices rise further. I bumped into a supplier yesterday who mentioned other projects are seeing similar increases.
Fergus: What are the options to manage that risk?
Nick: We recommend securing the remaining steel order this week to lock in current prices. And maybe consider bulk buying coffee for the team - it boosts morale.
Fergus: I’m happy to approve the steel, as long as it doesn’t affect cash flow too much. Not sure about the coffee though, unfortunately!
Robert: Thank you. We’ll proceed with placing the steel order.
Megan: Regarding design, the local council sent some further advice on the landscaping nearby, which I’ve noted, but it doesn’t impact our plan. Fergus, I know you have requested additional meeting rooms on level three. This will require a minor layout change but won’t affect the structure.
Fergus: Will that impact any deadlines on the project?
Megan: No, as long as we finalise the design changes by the end of this week. Robert: Can we agree that the updated drawings will be issued by Friday?
Megan: Yes, I’ll ensure they are sent out by then.
Fergus: That sounds fine. Please keep me informed if this does delay things.
Robert: To summarise, the project is on schedule, within budget, and we’ve agreed to secure steel materials and proceed with the design update. Our next progress meeting will be held in four weeks.
All: Agreed.

## Slide 3
Developing Experts Copyright 2026 All Rights Reserved
VWE: Morgan Sindall Construction – Day 3
Handout 1 – Taking minutes
Meeting minutes proforma
Project: _________________________
Date: ___________________________
Attendees: ____________________________________________________________ _______________________________________________________________________
Purpose of meeting:
_______________________________________________________________________
1. Progress updates/key points: _____________________________________________________________________________________________________________________________________________________________________________________________________________________
2. Issues/delays/challenges:
_____________________________________________________________________________________________________________________________________________________________________________________________________________________
3. Decisions made:
_____________________________________________________________________________________________________________________________________________________________________________________________________________________
4. Actions/tasks: Action: __________________________________________ Person responsible: _______________ Deadline: __________
Action: __________________________________________
Person responsible: _______________ Deadline: __________
Action: ___________________________
Person responsible: _______________ Deadline: __________
5. Next meeting:
Date: _____________________________