## Slide 1
Read through the information below. It tells you how long each element of the build is likely to take. Remember, allowance must be made for any delays on the project.
Developing Experts Copyright 2026 All Rights Reserved
VWE: Morgan Sindall Construction – Project Day
Handout 4 – Timeline
Your task is to create a 60 week timeline. You can do this on paper, using a spreadsheet, or on a digital document.
Think about using colours to represent the different stages of the build; you will need to include a key if you do.
Identify on your timeline when each task will happen and identify if any tasks overlap.
Show on your timeline how and when you will allow for any delays.
Task | Duration | Cannot start until…
Site setup | 4 weeks | N/A
Foundations | 6 weeks | Site setup finished
Timber frame | 10 weeks | Foundations finished
Roof | 4 weeks | Structural frame finished
External walls and windows | 6 weeks | Structural frame finished
First fix (plumbing and electrics) | 8 weeks | Structural frame finished
Internal walls | 6 weeks | First fix started
Second fix | 6 weeks | Internal walls finished
Internal finishes | 8 weeks | Second fix finished
Landscaping | 6 weeks | External walls finished

## Slide 2
Read through the information below. It tells you how long each element of the build is likely to take. Remember, allowance must be made for any delays on the project.
Developing Experts Copyright 2026 All Rights Reserved
VWE: Morgan Sindall Construction – Project Day
Handout 4 – Timeline Answers
The student’s timeline should show the following:
Site setup: Weeks 1–4
Foundations: Weeks 5–10
Timber frame: Weeks 11–20
Roof: Weeks 21–24
External walls: Weeks 21–26
First fix: Weeks 21–28
Internal walls: Weeks 21–26 (can overlap after first fix starts)
Second fix: Weeks 27–32
Internal finishes: Weeks 33–40
Landscaping: Weeks 27–32
Students can present this information in any way they like. They may have drawn a timeline and used colour to show the tasks, or done something similar digitally, perhaps using a spreadsheet. They should also show that the project is due to finish by Week 40, allowing 20 weeks of contingency for any delays.